IMPLEMENTATION PLAN  FOR B.Sc (HONS) DEGREE PROGRAM OF AGRONOMY

| AT Findings | Corrective Action | Implementation Date | Responsible Body | Resources Needed |
| --- | --- | --- | --- | --- |
| Criterion -3 Lab & Computing Facilities Lack of advance lab equipments. | Purchase of modern and advanced laboratory equipments for research. | 2011-2012 | Chairman | Advanced laboratory equipments. |
| Criterion-7 Institutional facilities Insufficient classrooms | Establishment of well-equipped classrooms. | 2011-2012 | Chairman/DoW | Space, multimedia, whiteboard, chairs and sound system. |
| Insufficient offices | Offices for faculty members needs to be provided. | 2011-12 | Chairman | offices needed. |
| No departmental seminar room/committee room | PC-1 should be prepared. | 2011-2013 | Chairman/Dow | Fund required. |
| No trained lab technicians | Hiring of trained lab technicians. | 2011-2013 | Chairman/Registrar | Human resource. |
| Lack of supporting Staff | Reshuffle/ transfer from other departments/sections. | As soon as possible | Chairman/Registrar | List should be provided to the Registrar office. |