IMPLEMENTATION PLAN FOR M.SC (HONS) DEGREE PROGRAM

OF HUMAN NUTRITION DEPARTMENT

| AT Findings | Corrective Action | Implementation Date | Responsible Body | Resources Needed |
| --- | --- | --- | --- | --- |
| Criterion 1: (Vision Mission Objectives) The Program outcomes for M.Sc (Hons) degree program is not documented. | Program outcomes should be defined and approved from relevant body and to make it in documented form. | As soon as possible | Chairman HN and Program Team members. | Nil |
| Criterion 1: All Ten proformae are not used for evaluation. | Evaluation through all ten proformae where applicable should be done periodically. | From next semester onward. | Chairman HN and Program Team members. | All ten Proformae |
| Criteria 3: (Laboratory and Computing Facility) No computer lab available in the department. Provision of computers and IT facilities | Project proposal should be submitted for establishment of computer lab. | 2013 | Chairman HN | Funds for establishment of advance computers and IT facilities. |
| Criteria 7: (Institutional Facilities) Space problem; class rooms are insufficient | Directorate of Teaching should be contacted for provision of required number of classrooms. | As soon as possible | Chairman HN/ Director Teaching | Space and Well-equipped classrooms. |
| Criteria 3: (Laboratory and Computing Facility) Lack of support personnel for labs. | Existing staff should be trained and if possible hire technical person for lab. | 2012-2013 | Human Nutrition / Registrar | Resource person/HR. |

| Criteria 6 Faculty: High qualified Faculty recruitment is needed. | Hiring of high qualified staff. | 2013 | Chairman HN/ Registrar | Human Resource |  |
| --- | --- | --- | --- | --- | --- |
| No research officer | Appointment of Research officer | 2013 | Chairman HN/ Registrar | Human Resource |  |
| Chairman’s Comments: The above AT findings are reasonable and need prompt action. Name: Prof. Dr. Saleem Khan Signature: ___________________________ |  |  |  |  |  |
| Dean’s Comments: Implementation plan is reasonable and corrective action needs to be done as soon as possible to overcome the weaknesses. Name: Prof. Dr. Alam Zeb Signature: ___________________________ |  |  |  |  |  |
| QEC’s Comments: The above findings are valid and need necessary action. Name: Prof. Dr. Farman Ullah Signature: ___________________________ |  |  |  |  |  |