IMPLEMENTATION PLAN FOR M.Sc(HONS) DEGREE PROGRAM

OF PLANT BREEDING & GENETICS DEPARTMENT

| AT Findings | Corrective Action | Implementation Date | Responsible Body | Resources Needed |
| --- | --- | --- | --- | --- |
| IT Trainings required | Course to be designed keeping in view the requirements of the students and to be approved by the Academic Council | Fall semester 2010 | Chairman/Subject specialist | Nil |
| Usage of Latest Software for Data Analysis | Latest data analysis software to be introduced in the course work | Spring semester 2010 | Chairman/Subject specialist | Rs. 100,000/- |
| New labs needed for undergraduate and post graduate students | PC-1 to be prepared | Fall 2011 | Chairman/P&D/Finance Deptt/HEC | Rs. 4 million |
| Latest Lab equipments & chemicals needed | PC-1 to be prepared | Fall 2010 | Chairman/P&D/Finance Deptt | Rs. One million |
| Greenhouses needed | PC-1 to be prepared | Fall 2012 | Chairman/ P&D/ Finance/HEC | Rs. 10 million |
| Shortage of class rooms | Ready to be handed over | Fall 2009 | - | - |
| Insufficient funds for conducting lab experiments | Proposal be prepared and submitted to DF | Spring 2010 | Chairman/Director Finance | As per requirement of the deptt. |