HIGHER EDUCATION COMMISSION

QUALITY ASSURANCE AGENCY (QAA)

Reporting period

| From |  |  |  | To |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Day | Month | Year | Day |  | Month | Year |
| 16 | October | 2009 | 15 |  | January | 2010 |

Title

- Name of the Project:				Quality Enhancement Cell

- Institution/Organization: 	NWFP Agricultural University Peshawar

- Name of report writer:	(i) Prof. Dr. Muhammad Afzal

(ii) Fouzia Bangash

- Postal Address:		Suite # 150, 1st Floor, NWFP Agricultural University,

Peshawar.

- Telephone/Fax/E-mail    	091- 9218612/ 091-9218342/

afzal@aup.edu.pk , fouzia@aup.edu.pk,

qec@aup.edu.pk

2.	Status of establishment of QEC office

- A separate QEC office established: ( Yes )

If No,

- Reasons

- Actions taken for the establishment of office

3.	Current update on the new recruitments made

Staff recruited

- Number of staff recruited:

No additional recruitment is made, since the QEC was made regular program of the University under recurring budget. All the previous staff per detail given below was allowed to keep continue their duties on their respective positions:

i. Prof. Dr. Muhammad Afzal	 Director Teaching/QEC  (additional charge basis)

ii. Ms. Fouzia			 Assistant Director Teaching/QEC

iii. Mr. Muhammad Bilal		 Data Analyst

iv. Mr. Waqas			 Office Assistant

v. Mr. Bilal Ahmad		 Naib Qasid

- Number of post advertised:

Please refer to 2nd Progress Report of Quality Enhancement Cell (QEC) submitted in March 2008 as the required information has already been submitted in the said report.

- Date of Publication of advertisement. (Attach copy of all advertisement):

Please refer to 1st Progress Report of Quality Enhancement Cell (QEC) submitted in October 2007 as the required information has already been submitted in the said report.

- List of short listed candidates:

Please refer to 2nd Progress Report of Quality Enhancement Cell (QEC) submitted in March 2008 as the required information has already been submitted in the said report.

- C.V. of the selected candidates:

Please refer to 2nd Progress Report of Quality Enhancement Cell (QEC) submitted in March 2008 as the required information has already been submitted in the said report.

- Terms and conditions/TORs of the recruited staff:

Please refer to 2nd Progress Report of Quality Enhancement Cell (QEC) submitted in March 2008 as the required information has already been submitted in the said report.

- Recruitment procedure:

Please refer to 2nd Progress Report of Quality Enhancement Cell (QEC) submitted in March 2008 as the required information has already been submitted in the said report.

- Salary being offered to the candidate:

Please refer to 2nd Progress Report of Quality Enhancement Cell (QEC) submitted in March 2008 as the required information has already been submitted in the said report.

If no selections made

- Status of temporary/permanent arrangement

- Appointment date

- Terms and conditions /TORs

- Salary being offered to the candidate

- Actions taken for the recruitment of permanent staff

- It will be appreciated if HEC is involved in short listing and recruitment process of Head of QEC

4.	Steps on development and implementation of QA mechanisms/procedures at the University during the reporting period

- Status of Self Assessment Mechanism being adopted at the university departments.

The process of Self Assessment is being implemented in the NWFP Agricultural University, Peshawar. In this regard, program teams were formulated in all the Departments/Institutes of the University who were given a formal training on the process of Quality Assurance with special emphasis on Self Assessment of the respective Department/Institute.

In the 1st phase, Department of Plant Breeding and Genetics (PBG) was selected as the Model Department. The process of Self Assessment was completed at PBG with their case being sent to the National Agriculture Education Accreditation Council (NAEAC) in June 2009. The report of NAEAC is still awaited. Currently, the Self Assessment Reports of Department of Soil and Environmental Sciences (SES) and Department of Plant Pathology are being examined and in this regard, meetings will be held with the above mentioned Departments to finalize the reports.

All the Departments/Institutes have started collection of data using the set of SA Proforma in order to incorporate it in their respective SARs.

b)   Update on selection of departments for establishment of Self Assessment Documentation.

Department of Plant Breeding & Genetics (PBG) was taken as model department to assess their program. Self-Assessment Report was finalized by the QEC and sent to the Assessment Team for further evaluation and after their review of the SAR, they submitted their recommendations to the QEC in April 2009. This case was then forwarded to the National Agriculture Education Accreditation Council (NAEAC) whose Accreditation Inspection Committee (AIC) visited the model Department. The final report of AIC is still awaited.

Two Departments namely Department of Soil and Environmental Sciences and Department of Plant Pathology have submitted their final SARs which are currently examined by QEC. Department of Food Science and Technology and Department of Rural Sociology have also submitted their initial draft reports.

c).	Status of formation of the team/committees involved in the process of Self Assessment:

The Program Teams have been formulated in all the Departments/Institutes of this University and the process of Self-Assessment has been started.

Assessment Teams have been formulated for the following Departments:

- Department of Plant Breeding and Genetics.

- Departrment of Soil & Environmental Sciences

- Department of Plant Pathology.

  - Updated list of members of the Program Teams (Annexure-1) /Assessment Teams (Annexure-2) / departmental committees

- If no team/Committee constituted, please specify the reasons and submit the action plan with time frame for the constitution of  the teams/committees (not applicable)

d).   Practical application of all the self assessment Proformae provided by HEC (Attach copy of Proformae) and status of their application. Update on

- Development / restructure/ modification of assessment Proforma for maximum data collection

Currently no major changes or modifications have been made in the proformas (Annexure-3). However, QEC in future plans to convert these proformas into digital form and place them online for the students to give their feedback.

- Number, type and date of Proformae circulated

| S.No | Departments / Institutes | Name & No. of Proforma / Manual | No. of Copies |
| --- | --- | --- | --- |
|  | Soil and Environmental Science | Teacher Evaluation Forms | 654 |
|  |  | Student’s Course Evaluation form | 654 |
|  | Water management | Self Assessment Manual | 03 |
|  |  | Survey of Graduating Students -03 | 100 |
|  |  | Employer Survey – 08 | 50 |
|  |  | Alumni Survey – 07 | 60 |
|  |  | Faculty Survey – 05 | 60 |
|  |  | Faculty Resume – 09 | 60 |
|  | Animal Nutrition | Research student progress review form - 04 | 20 |
|  |  | Faculty Course Review Report - 02 | 05 |
|  |  | Teacher Evaluation – 10 | 400 |
|  |  | Faculty Survey – 05 | 05 |
|  |  | Students Course Evaluation – 01 | 400 |
|  | Water Management | Self Assessment Manual | 03 |
|  |  | Survey of Graduating Students -03 | 100 |
|  |  | Employer Survey – 08 | 50 |
|  |  | Alumni Survey – 07 | 100 |
|  |  | Faculty Survey – 05 | 15 |
|  |  | Faculty Resume – 09 | 15 |
|  | Horticulture | Self Assessment Manual | 03 |
|  |  | Survey of Graduating Students -03 | 40 |
|  |  | Employer Survey – 08 | 150 |
|  |  | Alumni Survey – 07 | 150 |
|  |  | Faculty Survey – 05 | 12 |
|  |  | Faculty Resume – 09 | 15 |
| 6. | Agricultural Chemistry | Teacher Evaluation Forms | 150 |
|  |  | Student’s Course Evaluation form | 150 |
| 7. | Live Stock Management | Teacher Evaluation Forms | 700 |
| 8. | Agronomy | Teacher Evaluation Forms | 300 |
|  |  | Student’s Course Evaluation form | 100 |
|  |  | Research Student Progress Review | 50 |
| 9. | Weed Science | Teacher Evaluation Forms | 600 |
|  |  | Student’s Course Evaluation form | 600 |
| 10. | Maths,Statistics & Computer Sicence | Teacher Evaluation Forms | 1475 |
|  |  | Student’s Course Evaluation form | 1475 |
| 11. | Islamiyat & Pak. Studies | Teacher Evaluation Forms | 460 |
|  |  | Student’s Course Evaluation form | 460 |
| 12. | Entomology | Teacher Evaluation Forms | 210 |
|  |  | Student’s Course Evaluation form | 210 |
| 13. | Agricultural Mechanization | Teacher Evaluation Forms | 800 |
| 14. | Plant Pathology | Teacher Evaluation Forms | 550 |
|  |  | Student’s Course Evaluation form | 550 |
| 15. | Poultry Science | Teacher Evaluation Forms | 350 |
|  |  | Student’s Course Evaluation form | 350 |
| 16. | Plant Breeding & Genetics | Teacher Evaluation Forms | 1000 |
|  |  | Student’s Course Evaluation form | 1000 |
| 17. | Plant Protection | Teacher Evaluation Forms | 53 |
|  |  | Student’s Course Evaluation form | 53 |
| 18. | Institute of Bio-technology and Genetics Engineering | Teacher Evaluation Forms | 400 |
|  |  | Student’s Course Evaluation form | 400 |

- Information/feed back//data collected

The data for Spring Semester 2009 was collected by the Program Teams of all the Departments/Institutes which were submitted to QEC for analyses.

- Update on the evaluation of the feed back and development of Database.

QEC has developed a database for analysis and generation of results, for the different proformas. All the questions are given weights on the basis of the responses received from the students/faculty, display Score Card, Average Score in Percent (%), and display Pie Charts regarding each question

- Plan for further use of the information obtained.

The results generated by analysis of different Proformas are submitted to the Vice Chancellor, concerned Deans, Chairmen and Directors and is currently used by each Department/Institute for preparation of their respective Self-Assessment Report according to the self prescribed format given in the HEC’s Self-Assessment Manual.

These results have been useful in the selection of Best Teacher Award. This data has also been used in the ACRs and during the selection board of the faculty.

- In case no/some Proformae are not yet circulated, then specify the reasons and submit the time frame for the circulation of all/ remaining Proformae, collection of information and further processing (Not Applicable)

- Internal workshops organized by QEC during the reporting period at department/ university level for awareness /orientation of faculty

  - Date and number of events

  - Name of events

  - Participants of the event

  - Purpose of the event

  - (Attach copy of report)

- Workshops/ Trainings/ Meetings attended by QEC during reporting period at national /international level for awareness on the subject.

- Assistant Director Teaching/QEC attended a two days workshop on “Program Outcomes” held on 15-16 April, 2009 in Lahore.

- Assistant Director Teaching/QEC attended 12th meeting of the QECs held on 29-30 April, 2009 in Multan.

- Director Teaching/QEC and Assistant Director Teaching/QEC attended a two days “National Conference on Public Private Partnership for Higher Education” held on 25-26 May, 2009 in Islamabad.

- Director Teaching/QEC attended the 13th meeting of the QECs held on 18-19 August, 2009 in Karachi.

- Actions taken by QEC for sharing/ application of the knowledge gained by QEC during the workshops at HEC

The knowledge and experience sharing is disseminated with the faculty as well as students during different meetings held with these stakeholders from time to time.

- QEC website development and information uploaded

A separate link (http://www.aup.edu.pk/QEC.php), developed in the NWFP Agricultural University, Peshawar, website is updated on regular basis to keep the information related to Quality Assurance accessible.

- Detail of expenditures made by QEC during the reporting period duly vet by the concerned Audit and account section

In compliance to HEC, Islamabad Policy letter No. 1/QEC/QAA/HEC/07-323 dated June 02, 2008; the Quality Enhancement Cell (QEC) has become a regular part of the University and all the expenses required for the smooth running of QEC are now met by the University recurring budget w.e.f. July 01, 2008 (Annexure-4)

6.	Accomplishments during the Reporting Period

Accomplishments of the Quality Enhancement Cell (QEC), NWFP Agricultural University, Peshawar during this Quarter.

| S. No. | Month/Year | Activity | Remarks |
| --- | --- | --- | --- |
|  | October, 2009 | Finalization of Self-Assesment Report (SAR) of Departments of Soil & Environemtal Sciences (SES) and Plant Pathology. | Done |
|  | October-November, 2009 | Finalization of undergraduate admission for the session 2010. | Done |
|  | November, 2009 | Formulation of Assessment Team (AT) for Departments of Soil & Envonemntal Sciences (SES) and Plant Pathology | Done |
|  | December, 2009 | Meeting with Department / Institutes regarding Self Assessment Report | Done |
|  | December, 2009 | Collection of Teacher and Course Evaluation Forms for Fall semester 2009 | Done |
|  | January 2010 | Criteria based evaluation of SARs, by Assessment Teams (AT) of SES and Plant Pathology. | Done |
|  | January 2010 | Orientation for the newly inducted students of the undergraduate program. | Done |
|  | November 09 - January 2010 | Collection of subject level database proforma I & II for HEC. | Done |
|  | November 09 - January 2010 | Collection of S&T Database for Pakistan Council for Science and Technology, Islamabad. | Done |
|  | November-December, 2010 | Attended a meeting regarding Anti_Plagiarism through video conferencing. | Done |
|  | January 2010 | Meetings with SES and plant pathology Departments. | Done |